## Version 1
|  | 2024-10-23 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-20 | 2024-11-27 | 2024-12-04 | 2024-12-11 | 2024-12-18 | 2024-12-25 | 2025-01-01 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-29 | 2025-02-05 | 2025-02-12 | 2025-02-19 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28
|  | semaine 1 | semaine 2 | semaine 3 | semaine 4 | semaine 5 | semaine 6 | semaine 7 | semaine 8 | semaine 9 | semaine 10 | semaine 11 | semaine 12 | semaine 13 | semaine 14 | semaine 15 | semaine 16 | semaine 17 | semaine 18 | semaine 19 | semaine 20 | semaine 21 | semaine 22 | semaine 23 | semaine 24 | semaine 25 | semaine 26 | semaine 27 | semaine 28 | semaine 29 | semaine 30 | semaine 31 | semaine 32
Théorie | Better understading of the topic + Goal definition + find implementation | [13 empty] | 2025-05-07: correction report (+ Presentation preparation)
Quantum (Notion)
Quantum (Shor)
Quantum (Grover)
Quantum (Regev)
Quantum (how far is the quantum computers currently ?, the risk, ...)
Embedded system ( Notion )
Embedded system ( Challenge )
Embedded system ( MQTT )
Cryptography (overview )
Cryptography ( use in embedded system)
Cryptography (ML-KEM [CRYSTALS-KYBER])
Cryptography (ML-DSA [CRYSTALS-DILITHIUM])
Cryptography (SLH-DSA [sphinc+])
State of the art ( current research )
Explain SUPERCOP ( + computer notion)
Introduction
Pratique | Discussion about key size, outpout, … between PQC and standard crypto on MQTT | bar: 2025-01-22
Presentation + comparaison between implementation ( based on results of SUPERCOP ) | bar: 2025-01-29 to 2025-02-12
How to take measurment ( explanation tools + set up) | bar: 2025-02-19
Set up MQTT experimentation | bar: 2025-02-26
data collection (1) | bar: 2025-03-05
Data analysis (1) | bar: 2025-03-05 to 2025-03-12
Implementation (SLH-DSA, python) | bar: 2025-03-19 to 2025-04-09
data collection (2) | bar: 2025-04-16
Data analysis (2) | bar: 2025-04-16 to 2025-04-23
Discussion | bar: 2025-04-30
Conclusion | bar: 2025-04-30
Futur work | bar: 2025-04-30

## Version 2
|  | 2024-12-18 | 2024-12-25 | 2025-01-01 | 2025-01-08 | 2025-01-15 | 2025-01-22 | (approximate date) New version algorithm | 2025-01-29 | 2025-02-05 | 2025-02-12 | End Part 1 | 2025-02-19 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | Deadline for deposit with signed aprproval by promotor (01/06/24)
|  | week 0 | week 1 | week 2 | week 3 | week 4 | week 5 |  | week 6 | week 7 | week 8 |  | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20 | week 21 | week 22 | week 23
| Writing thesis | [11 empty] | 2025-05-21: Safety week for schedule delays
Part 1 | Implementation of remote attestation protocol
Evaluation of algorithms on protocols
Data analysis + critique of different algorithms
Part 2 | Premilary Analysis of SQIsign and find best board | [6 empty] | Board order
Study of SQIsign ( algorithm + code ) | bar: 2025-02-19 to 2025-03-05
Analysis GMP | bar: 2025-03-19 to 2025-03-26
Update SQIsign for GMP | bar: 2025-04-09 to 2025-04-16
Update SQIsign for dynamic memory allocations | bar: 2025-04-30
Testing SQIsign on board | bar: 2025-05-07 to 2025-05-14